## 2018 Timeline
DEDP-Launching 2018
| Activity | Target Date | Functional Division In-charge | Outputs
1 | Finalization (Division level) | March 2018 (March 1-28, 2018) to 1st & 2nd Week of April (April 2-13, 2018) | SDO (CID, SGOD, OSDS) | DEDP Final draft
2 | Organizational Capacity: DO Mobilization (Tasking, Structure, Terms of Reference, IPCRF, Contract Signing, etc.) | 3rd week of April (April 16-20, 2018) | SDO (CID, SGOD, OSDS) | Tasking, Structure, Terms of Reference, IPCRF, Contract Signing Finalized
3 | Endorsement to Region | 4th week of April (April 23-27, 2018) | SDO (SGOD) | DEDP Final draft submitted
4 | Approval by the Regional Director | 1st week of May 2018 (May 1-4, 2018) | RO (PPRD) | Approved DEDP
5 | Pledging Sessions | 2nd Week of May 2018 (May 7-11, 2018) | SDO (CID, SGOD, OSDS) | MOA/Pledges/Agreements Signed
6 | DEDP Launching | 3rd Week of May 2018 (May 14-18, 2018) | SDO (CID, SGOD, OSDS) | DEDP advocacy conducted
7 | DEDP Start Up | 4th week of May 2018 (May 21-25, 2018) | SDO (CID, SGOD, OSDS) | DEDP mobilization report submitted
8 | DEDP Implementation (Official Start Date) | 1st week of June 2018 (June 4-8, 2018) | SDO (CID, SGOD, OSDS) | DEDP implementation commenced
9 | School/District MEA | 1st 2 weeks of the last month of the quarter of CY | SDO (CID, SGOD, OSDS) | MEA report submitted/ accepted
10 | Division MEA | 3rd week of the last month of the quarter of CY | SDO (CID, SGOD, OSDS) | MEA report submitted/ accepted / PPAs adjusted
11 | Regional MEA | 4th week of the last month of the quarter of CY | RO (QAD) | MEA report submitted/ accepted / PPAs adjusted
12 | Regional Technical Assistance Conference | 2nd week after the last month of the quarter of CY | RO (FTAD) | TA Plan submitted/accepted
13 | Annual Program Implementation Review (PIR)/4th QTR RMEA | 3rd week of the last month of the CY (December) | RO (QAD) | PIR report submitted/ accepted / PPAs adjusted

## 2018 Time Table
Item | Activity | 1st Quarter | [11 empty] | 2nd Quarter | [11 empty] | 3rd Quarter | [11 empty] | 4th Quarter
|  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
|  | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4
1 | Finalization (Division level) | bar: March Week-1 to April Week-2
2 | Organizational Capacity: DO Mobilization (Tasking, Structure, Terms of Reference, IPCRF, Contract Signing, etc.) | bar: April Week-3
3 | Endorsement to Region | bar: April Week-4
4 | Approval by the Regional Director | bar: May Week-1
5 | Pledging Sessions | bar: May Week-2
6 | DEDP Launching | bar: May Week-3
7 | DEDP Start Up | bar: May Week-4
8 | DEDP Implementation (Official Start Date) | bar: June Week-1
9 | School/District MEA | bar: March Week-1 to March Week-2; June Week-1 to June Week-2; September Week-1 to September Week-2; December Week-1 to December Week-2
10 | Division MEA | bar: March Week-3; June Week-3; September Week-3; December Week-3
11 | Regional MEA | bar: March Week-4; June Week-4; September Week-4; December Week-4
12 | Regional Technical Assistance Conference | bar: April Week-2; July Week-2; October Week-2
13 | Annual Program Implementation Review (PIR)/4th QTR RMEA | bar: December Week-3